# Regenerative Neighborhood Framework

## Complete Hybrid Sequencing Model with Full Templates & Worksheets

Version 1.0 - Ready for Implementation

# TABLE OF CONTENTS

- Overview & Philosophy

- SPIRAL 1: Proof-of-Concept (0-6 months)

- SPIRAL 2: Feasibility Validation (3-12 months)

- SPIRAL 3: Capital Optimization (9-15 months)

- SPIRAL 4: Construction & Operation (12-36 months)

- SPIRAL 5: Continuous Regeneration (Year 2+)

- Appendix: All Worksheets & Templates

# PART 1: OVERVIEW & PHILOSOPHY

## The Hybrid Model at a Glance

This model combines three approaches:

- Conditions-Based Foundation - Flexibility in timing; clear prerequisites

- Integration Gates - Major decision points; go/no-go clarity

- Coherence Spirals - Iterative deepening; build → learn → improve

### Why This Works:

- Realistic: Acknowledges some activities take predictable time (land search) while others can accelerate

- Flexible: Multiple work streams happen in parallel where possible

- Safe: Major decisions only made when prerequisites are met

- Learning-Oriented: Each spiral provides opportunity to adapt before next phase

- Regenerative: Embeds feedback loops and continuous improvement

### Core Principle:

"Do reversible things first. Only make irreversible decisions when you absolutely must, and only after thorough validation."

## Timeline Overview (Best Case / Typical Case / Conservative)

| Phase | Best Case | Typical | Conservative |
| --- | --- | --- | --- |
| Spiral 1 | 3 months | 6 months | 8 months |
| Spiral 2 | 4 months | 9 months | 15 months |
| Spiral 3 | 3 months | 6 months | 9 months |
| Spiral 4 | 12 months | 24 months | 36 months |
| Total | 22 months | 45 months | 68 months |

Most realistic: 3-4 years from idea to occupancy

## Key Success Factors

- Experienced Facilitator - Someone who has built community before

- Clear Governance - Decisions made fast, not endlessly debated

- Realistic Timeline Expectations - Don't try to rush land search

- Strong Market Validation - Know people actually want this

- Early Culture Seeding - Start building community culture immediately

- Continuous Feedback - After each sprint, pause and learn

# SPIRAL 1: PROOF-OF-CONCEPT

## Months 0-6 | Goal: Validate Vision is Possible

Objective: Assemble core team, explore feasibility broadly, build shared commitment

Success Looks Like: Core team aligned, 3-5 viable bioregions identified, proof-of-concept design sketched, capital needs estimated

## SPIRAL 1: CONDITION SET 1

### Core Team & Vision Coherence

Timeline: Weeks 0-4

#### 1.1 ASSEMBLE CORE TEAM

Ideal Size: 5-7 founders (7-12 including broader circle)

Essential Roles in Founding Team:

- Visionary/Dreamer - Holds the "why" and inspiration

- Operator/Pragmatist - Makes things real, manages timelines

- Financial/Strategic - Understands economics and big picture

- Design-minded - Thinks about how things fit together

- Community/Heart - Focuses on relationships and culture

Worksheet 1.1.A: Founder Assessment

Founder Name: ___________________

Role/Strengths: _________________

Commitment Level: Full-time / Part-time / Advisory

Geographic Location: _______________

Why This Project? (personal story):

________________________________

Available Hours per Week: _____

Top 3 Skills to Contribute:

1. _____________________

2. _____________________

3. _____________________

Gaps/Learning Needed:

_____________________

Financial Capacity (check all that apply):

☐ Can invest $X in project

☐ Can work full-time without salary

☐ Can donate 10+ hours/week

☐ Can provide professional services (architecture, legal, etc.)

☐ Can provide space for meetings

☐ Other: _____________

Repeat for each founding team member

#### 1.2 ESTABLISH SHARED VISION

Worksheet 1.2.A: Individual Vision Interviews

Interview each founder separately, then together. Ask:

1. WHY are you drawn to regenerative community?

(Personal story, not ideology)

2. What problem are you trying to solve?

(For yourself / for community / for planet)

3. If this project succeeds beyond your wildest dreams,

what would that look like 10 years from now?

(Be specific - senses, daily life, impact)

4. What are your non-negotiables?

(Things that MUST be true for you to stay)

- Things that cannot be compromised on

- Things that are dealbreakers if violated

5. What are your fears/concerns about this project?

(Money running out? Wrong people? Failure?)

6. How much risk are you willing to take?

(On a scale: conservative, moderate, high-risk)

7. What's your timeline expectation?

(2 years? 5 years? 10 years?)

Synthesis Activity:

Hold a 4-hour founding circle where you:

- Share responses (vulnerably, authentically)

- Identify common themes

- Name differences (don't hide them)

- Negotiate on timeline & risk tolerance

- Identify what you're all actually trying to create

#### 1.3 IDENTIFY SHARED DECISION-MAKING APPROACH

Worksheet 1.3.A: Governance Preference Assessment

For each question, rate 1-5 (1=strongly disagree, 5=strongly agree):

DECISION-MAKING STYLE:

☐ We want to move fast (willing to make decisions with 70% certainty)

☐ We want consensus (everyone agrees or we keep discussing)

☐ We want efficient democracy (majority vote, minority heard)

☐ We want expertise-based (skilled person decides their domain)

COMMUNICATION STYLE:

☐ Direct/blunt is fine, honesty matters most

☐ Gentle/diplomatic, preserving relationships matters

☐ Hybrid - direct but kind

CONFLICT APPROACH:

☐ Address immediately when it comes up

☐ Take time, process with a neutral party

☐ Work it out in writing first, then discuss

☐ Keep it private, not in group

POWER DISTRIBUTION:

☐ Equal voice for all co-founders

☐ Distributed by expertise in that area

☐ One person leads, others follow

☐ Rotating leadership

TIMELINE:

☐ Move fast (decide within 1 meeting)

☐ Normal pace (2-3 meetings to decide)

☐ Take time (multiple discussions, research)

FINANCIAL DECISIONS:

☐ Everyone puts in equal amounts

☐ Each invests what they can afford

☐ Outside investors lead; founders follow

☐ Hybrid - founders have veto power

Synthesis: Notice patterns. Where do you align? Where do you differ? Are differences dealbreakers?

#### 1.4 DOCUMENT SHARED VALUES STATEMENT

Template 1.4.A: Founding Values Statement

PROJECT NAME: _______________________

DATE: ______________

FOUNDING TEAM: (list names)

OUR REGENERATIVE COMMITMENT:

(2-3 sentences on what regeneration means to us)

___________________________________

___________________________________

___________________________________

OUR COMMUNITY VISION:

(What will daily life feel like? Who are we? What's unique about us?)

___________________________________

___________________________________

___________________________________

OUR NON-NEGOTIABLES:

(What cannot be compromised - the 3-5 things that define us)

1. _________________________________

2. _________________________________

3. _________________________________

4. _________________________________

5. _________________________________

OUR OPERATING PRINCIPLES:

(How we make decisions, treat each other, relate to land/community)

1. _________________________________

2. _________________________________

3. _________________________________

OUR TIMELINE EXPECTATION:

(Realistic acknowledgment of pace we're willing to move)

- Land secured by: __________ (realistic year)

- Occupancy target: __________ (realistic year)

- Full vision realized: __________ (realistic year)

OUR FINANCIAL PHILOSOPHY:

(What does regeneration mean economically for us?)

___________________________________

___________________________________

SIGNED (representing group alignment):

_______________________

_______________________

_______________________

This is your founding document. Reference it constantly.

#### 1.5 ESTABLISH COMMUNICATION & DECISION INFRASTRUCTURE

Worksheet 1.5.A: Decision-Making & Communication System Design

TEAM MEETINGS:

☐ Weekly (day/time): ________________

☐ Bi-weekly (day/time): ________________

☐ Monthly (day/time): ________________

FORMAT:

☐ In-person ☐ Hybrid ☐ Virtual

☐ Location/Platform: _______________

DECISION PROTOCOL:

☐ How long to discuss: _____________

☐ Voting method: _________________

☐ Who decides: __________________

☐ Documentation: ________________

COMMUNICATION CHANNELS:

☐ Email list: ___________________

☐ Chat (Slack/WhatsApp): __________

☐ Document sharing (Google Drive/GitHub): ________

☐ Project management (Asana/Trello): __________

DECISION DOCUMENTATION:

All decisions recorded with:

- Date & who decided

- What was decided

- Why (reasoning)

- Who dissented (and why)

- Next review date (if applicable)

CONFLICT PROTOCOL:

If disagreement: ___________________

If deadlock: ____________________

Neutral facilitator: ________________

### SPIRAL 1: GATE 1 CHECKPOINT

## "Core Team Coherence"

Decision Point: Is the team ready to explore further?

Exit Criteria - ALL MUST BE TRUE:

☐ 5-7 people committed to founding team ☐ Written shared values statement signed by all ☐ Decision-making approach agreed and documented ☐ Communication systems established and working ☐ All team members have articulated their personal "why" ☐ Non-negotiables identified and negotiated (no dealbreaker conflicts) ☐ Financial commitment clear (who's investing what) ☐ Realistic timeline expectations aligned

Gate 1 Go/No-Go Decision:

GATE 1 ASSESSMENT:

Date: __________

Facilitator: __________

Condition 1 - Team coherence: ☐ YES ☐ NO ☐ PARTIAL

Specific evidence: _____________________________

Condition 2 - Shared vision: ☐ YES ☐ NO ☐ PARTIAL

Specific evidence: _____________________________

Condition 3 - Governance clarity: ☐ YES ☐ NO ☐ PARTIAL

Specific evidence: _____________________________

GATE 1 DECISION:

☐ PROCEED to Condition Set 2 (Market & Feasibility)

☐ PAUSE - need more team alignment work (timeline: ____)

☐ STOP - cannot proceed with current team

If PAUSE: What specific work is needed? __________________

Timeline: ______________

Responsible person: __________

Next checkpoint: __________

## SPIRAL 1: CONDITION SET 2

### Market & Feasibility Exploration

Timeline: Weeks 2-24 (parallel with Condition Set 1, but intensive after Gate 1)

Goal: Is there demand for this? Is it ecologically and economically viable? Has someone done this successfully before?

#### 2.1 DEFINE TARGET COMMUNITY PROFILE

Worksheet 2.1.A: Community Identity Clarity

COMMUNITY TYPE (check all that apply):

☐ Residential ecovillage

☐ Farm/permaculture community

☐ Spiritual/contemplative community

☐ Arts/creative hub

☐ Intentional co-living

☐ Wellness retreat center

☐ Education center

☐ Mixed/hybrid

IDEAL SIZE RANGE:

☐ Small (20-50 people)

☐ Medium (50-200 people)

☐ Large (200-500 people)

☐ Very large (500+)

MEMBER PROFILE - Who do we want to attract?

Primary demographic (age, background, skills):

________________________________

What lifestyle are they seeking?

________________________________

What problem do they want solved?

________________________________

Income level:

☐ Low-income ☐ Middle ☐ Mixed ☐ High-income

Geographic origin:

☐ Local only ☐ Regional ☐ International

Commitment level we're seeking:

☐ Permanent residents

☐ Short-term (seasonal)

☐ Both

☐ Rotating community

UNIQUE VALUE PROPOSITION:

What makes our community different/better than alternatives?

1. ____________________________

2. ____________________________

3. ____________________________

WHO WOULD PAY FOR THIS?

(How do members generate capital / where does revenue come from?)

____________________________

SUSTAINABILITY MODEL:

How will members sustain themselves economically?

☐ Individual income (remote work, local jobs)

☐ Community businesses (farm, retreat center, etc.)

☐ Hybrid

☐ Alternative (gift economy, etc.)

REGULATORY CONTEXT:

Where would this legally work?

☐ Urban ☐ Suburban ☐ Rural

☐ Intentional community zoning friendly

☐ Agricultural zoning

☐ Mixed use zones

☐ Need variance/special use permit

#### 2.2 MARKET VALIDATION

Worksheet 2.2.A: Demand Assessment

Task 1: Find Existing Communities with Similar Profile

Search for 5-10 communities that match your vision (use: IC.org, Cohousing.org, Ecovillage Network, Tribes Platform, local networks)

CASE STUDY RESEARCH:

Community Name: ________________

Location: __________________

Founded: ____  Current size: ____

Model: _____________________

Website/contact: ________________

Key questions to research/contact:

1. How long to populate?

2. What was total capital needed?

3. Are they financially sustainable?

4. What's the waitlist like?

5. What surprised them?

6. What would they do differently?

7. What's their revenue model?

Repeat for 5-10 communities

Task 2: Demand Interviews

Contact 20-30 people who match your "ideal member" profile. Ask:

INTERVIEW SCRIPT:

"I'm exploring starting a regenerative community focused on

[your focus]. I'm talking with people who might be interested

to understand what draws them to community living.

1. Are you currently interested in living in community?

☐ Very interested ☐ Somewhat ☐ Maybe ☐ No

2. What would make community appealing to you?

_________________________

3. What would make you say 'no'?

_________________________

4. If a community like ours existed now, would you consider it?

☐ Yes, definitely ☐ Maybe ☐ No

5. What timeline would work for you?

_________________________

6. What could you contribute (money, skills, labor)?

_________________________

RESULT: ___ interested / ___ somewhat / ___ not interested

"

Analysis:

MARKET VALIDATION SUMMARY:

Total interviews conducted: ____

Percent "definitely interested": ____%

Percent "maybe interested": ____%

Percent "not interested": ____%

Is there demand?

☐ YES - clear interest from ___+ people

☐ MAYBE - interest but not certain

☐ NO - minimal interest

What are people most attracted to?

________________________________

What are their biggest hesitations?

________________________________

Realistic projection:

- In 5 years, we could attract: ____ people

- They would have: ____% commitment to move in

- Realistic first cohort: ____ people

#### 2.3 BIOREGIONAL FEASIBILITY

Worksheet 2.3.A: Bioregional Match Analysis

Task 1: Identify 3-5 Potential Bioregions

Consider:

- Climate compatibility with your vision

- Water availability patterns

- Regulatory friendliness to community living

- Cost of land

- Proximity to members

- Cultural/ecological alignment

BIOREGION #1: _______________

Location (state/country): ________

Climate: _________________

Water availability: _________

Regulatory environment: ______

Land cost range: __________

Distance from members: ________

Why this region? ___________

BIOREGION #2: _______________

[repeat above]

BIOREGION #3: _______________

[repeat above]

BIOREGION #4: _______________

[repeat above]

BIOREGION #5: _______________

[repeat above]

Task 2: Climate & Resource Viability Check

For each bioregion, research:

CLIMATE ANALYSIS:

- Annual rainfall: _______  (need: _______)

- Frost-free period: _______ (need: ______)

- Average temp range: _____

- Growing season: ________

- Extreme weather risks: _____________

WATER SYSTEMS:

- Water table depth: _______

- Surface water sources: ________

- Watershed health: ________

- Water law restrictions: __________

- Can support this community? ☐ Yes ☐ No ☐ Maybe

SOIL & FOOD:

- Soil type: _____________

- pH: _______

- Organic matter: _______

- Food security potential: ________

- Can feed this community? ☐ Yes ☐ No ☐ Maybe

ENERGY:

- Solar potential (kWh/sq meter): ______

- Wind resources: _________

- Hydro potential: ________

- Grid availability: ________

- Energy independence possible? ☐ Yes ☐ No ☐ Maybe

BIODIVERSITY:

- Dominant ecosystem: __________

- Threatened species: __________

- Restoration opportunities: __________

- Compatible with community? ☐ Yes ☐ No

REGULATORY ENVIRONMENT:

- Zoning for community? ☐ Yes ☐ No ☐ Possible with variance

- Environmental restrictions: __________

- Building codes compatibility: __________

- Community living legal? ☐ Yes ☐ No

- Easements/protections on land? __________

ECONOMIC VIABILITY:

- Land costs (per acre): $______

- Labor availability: __________

- Local business opportunities: __________

- Tourism potential: __________

- Remote work friendly (internet)? ☐ Yes ☐ No

#### 2.4 ECONOMIC VIABILITY SKETCH

Worksheet 2.4.A: Preliminary Financial Model

This is rough. Not final. Just testing if math works.

REVENUE STREAMS:

What will generate income? (Check all that apply)

☐ Real estate sales/lot sales

☐ Long-term rentals

☐ Short-term rentals (retreat center, AirBnB)

☐ Workshops/seminars

☐ Farm products

☐ Value-added products (jam, soap, etc.)

☐ Memberships/fees

☐ Business incubation fees

☐ Other: _______________

CAPITAL NEEDS - ROUGH ESTIMATE:

Land (per acre):

- ___ acres x $___/acre = $________

Infrastructure per person:

- Housing: $_______ x ___ people = $_______

- Water system: $_______ (fixed cost)

- Energy system: $_______ (fixed cost)

- Food system: $_______ (fixed cost)

- Waste system: $_______ (fixed cost)

- Roads/paths: $_______ (fixed cost)

- Common buildings: $_______ (fixed cost)

Total Infrastructure: $_________

Total per person: $________

Working capital (2 years operation): $_________

TOTAL CAPITAL NEEDED: $_________

FUNDING SOURCES - ROUGH ESTIMATE:

From residents (down payments): $_________

From investors (equity): $_________

From grants/impact capital: $_________

From loans: $_________

From founders: $_________

Total: $_________

Does it add up? ☐ Yes ☐ No ☐ Close

If NO, what's the gap? $________

How could you bridge it?

- Reduce scope? ☐ Yes/No

- Increase resident numbers? ☐ Yes/No

- Smaller housing units? ☐ Yes/No

- More commercial revenue? ☐ Yes/No

OPERATING ANNUAL BUDGET - ROUGH ESTIMATE:

Staff salaries: $_________

Maintenance & utilities: $_________

Insurance: $_________

Administration: $_________

Capital improvement reserve: $_________

Total annual: $_________

How will this be covered?

- Member fees: $_________

- Business revenue: $_________

- Other: $_________

Viable?  ☐ Yes ☐ No ☐ Needs work

#### 2.5 REGULATORY LANDSCAPE

Worksheet 2.5.A: Regulatory Feasibility

Contact local planning departments, zoning boards. Ask:

For each bioregion, research:

ZONING:

Current zoning: _____________

Allows multi-family residential? ☐ Yes ☐ No

Allows intentional community? ☐ Yes ☐ No

If no, can you get variance? ☐ Yes ☐ No ☐ Unknown

Variance process: _____________

Cost: $_______

Timeline: _______

ENVIRONMENTAL:

Environmental review required? ☐ Yes ☐ No

Endangered species issues? ☐ Yes ☐ No

Wetlands on property? ☐ Yes ☐ No ☐ Unknown

Historic sites? ☐ Yes ☐ No

UTILITIES:

Municipal water available? ☐ Yes ☐ No

Can use well? ☐ Yes ☐ No

Septic allowed? ☐ Yes ☐ No

Grid electricity required? ☐ Yes ☐ No

Natural gas available? ☐ Yes ☐ No

BUILDING:

Can build alternative structures (earthship, superadobe)?

☐ Yes ☐ No ☐ Only with variance

Can build smaller homes? ☐ Yes ☐ No

Minimum lot size? _______ acres

COMMUNITY OPERATIONS:

Can operate as co-op/commune? ☐ Yes ☐ No

Legal entity options available? ☐ Yes ☐ No

Can have community business on site? ☐ Yes ☐ No

Can host events/retreat center? ☐ Yes ☐ No

COMPLICATIONS:

Major regulatory barriers: __________

Surprising restrictions: __________

Friendly official to contact: __________

#### 2.6 PROOF-OF-CONCEPT DESIGN SKETCH

Worksheet 2.6.A: Minimal Viable Design

Quick sketch (not detailed) showing if your vision can fit on land.

POPULATION: ____ people

LAND NEEDED: ____ acres (calculate:

- Housing (0.1-0.25 acres per person): ___

- Food production (0.5-1 acres per person): ___

- Infrastructure/paths (0.1 acres per person): ___

- Conservation/undisturbed (remaining): ___

- TOTAL: ___)

HOUSING TYPE:

☐ Individual homes

☐ Apartment building

☐ Cohousing (mix)

☐ Yurts/domes/alternative

Average size per unit: ____ sq ft

Total housing sq ft: __________

COMMON SPACES:

☐ Community center/dining

☐ Kitchen

☐ Meeting rooms

☐ Workspace/coworking

☐ Arts/craft studio

☐ Guest accommodations

Total sq ft: __________

AGRICULTURAL:

☐ Food forest / perennial food

☐ Vegetable gardens

☐ Livestock area

☐ Composting facility

Total acres: __________

WATER SYSTEMS:

☐ Rainwater capture

☐ Wells

☐ Surface water

Treatment method: __________

Storage capacity: _________ gallons

ENERGY SYSTEMS:

☐ Solar (rooftop): ____ kW capacity

☐ Solar (ground mount): ____ kW capacity

☐ Wind: ____ kW capacity

☐ Micro-hydro: ____ kW capacity

Storage: _________ kWh

WASTE:

☐ Composting system

☐ Septic/treatment wetland

☐ Recycling facility

☐ Biodigestor

TRANSPORTATION:

☐ Pedestrian paths only

☐ Limited vehicle access

☐ Central parking area

Parking spaces: _____

SKETCH:

(Draw rough layout on paper, photo/scan)

[SPACE FOR SKETCH]

FEASIBLE? ☐ Yes ☐ No ☐ With modifications

What needs modification? __________________

### SPIRAL 1: GATE 2 CHECKPOINT

## "Feasibility Landscape"

Decision Point: Is this vision actually possible?

Exit Criteria - ALL MUST BE TRUE:

☐ 3-5 viable bioregions identified ☐ Market validation shows demand (minimum 10+ "definitely interested") ☐ Climate/water/soil analysis done for each bioregion ☐ Regulatory landscape mapped for each region ☐ Rough financial model sketched (shows capital needed) ☐ Proof-of-concept design fits on typical land size ☐ Team understands major obstacles (and they're not dealbreakers) ☐ Team confirms: "This is possible"

Gate 2 Go/No-Go Decision:

GATE 2 ASSESSMENT:

Date: __________

Facilitator: __________

Feasibility finding - Market demand: ☐ YES ☐ NO ☐ WEAK

Evidence: _____________________________

Feasibility finding - Bioregion viable: ☐ YES ☐ NO ☐ WEAK

Best region: _________ (why: _________)

Feasibility finding - Economics workable: ☐ YES ☐ NO ☐ TIGHT

Gap if any: $____________

Feasibility finding - Regulatory possible: ☐ YES ☐ NO ☐ WITH VARIANCE

Major barriers: _____________________________

GATE 2 DECISION:

☐ PROCEED to Spiral 2 (Land search + capital strategy)

☐ PIVOT - modify vision based on learnings (new timeline: ____)

☐ STOP - vision not feasible in current form

If PIVOT: What changes? __________________

New timeline: ______________

Responsible person: __________

## SPIRAL 1: SUMMARY & DELIVERABLES

Timeline: 0-6 months (can overlap; typical 4-6 months)

Key Deliverables Produced:

- ✓ Founding Team Roster (5-7 people, committed)

- ✓ Shared Values Statement (signed by all)

- ✓ Governance & Decision-Making Protocol (documented)

- ✓ Community Identity Profile (who we're building for)

- ✓ Market Validation Report (evidence of demand)

- ✓ Bioregion Feasibility Analysis (3-5 regions assessed)

- ✓ Preliminary Financial Model (capital needed estimated)

- ✓ Regulatory Landscape Summary (what's legally possible)

- ✓ Proof-of-Concept Design (sketch showing it fits)

Team Composition After Spiral 1:

- Core 5-7 founders all aligned

- Broader circle of 15-25 "interested parties"

- 20-30 market validation respondents identified

- 1-2 local government contacts in key regions

Budget Spent: $2,000-$10,000 (mostly meeting expenses, travel, consultant calls)

Ready for Spiral 2? YES → Proceed to Land Search & Capital Strategy

# SPIRAL 2: FEASIBILITY VALIDATION

## Months 3-12 | Goal: Specific Land + Specific Capital Pathway

Objective: Find real land, deepen team, plan realistic funding strategy

Success Looks Like: Land identified (optioned or purchased), team expanded, capital sources identified

## SPIRAL 2: CONDITION SET 3

### Specific Land Identification & Assessment

Timeline: Months 3-12 (often the longest single phase)

Philosophy: Don't rush land. It's the foundation of everything. Better to wait for the right land than be stuck with the wrong land.

#### 3.1 LAND SEARCH STRATEGY

Worksheet 3.1.A: Land Search Parameters

PRIORITY BIOREGION(S):

Rank by preference:

1. __________ (why: __________)

2. __________ (why: __________)

3. __________ (why: __________)

LAND SPECIFICATIONS:

Size Range: ____ to ____ acres

(rough calc: ___ people x 1-2 acres/person = ____ acres)

Budget: $________ to $________ total

Price per acre acceptable: $________ to $________

ESSENTIAL FEATURES (must-haves):

☐ Water source (spring, creek, good well potential)

☐ Southern exposure (for solar/passive solar)

☐ Good soil (for food production)

☐ Existing structures (reduces building costs)

☐ Road access

☐ Utilities available (or can be created)

☐ Zoning allows community development

Other: __________________

NICE-TO-HAVES:

☐ Existing buildings

☐ Already partially cleared

☐ Agricultural history

☐ View/aesthetics

☐ Distance to town

☐ Established relationships with neighbors

Other: __________________

DEAL-BREAKERS:

(Things that would make this wrong)

☐ Contaminated soil

☐ Flood zone

☐ Endangered species habitat

☐ Toxic neighbors (factory, etc.)

☐ Zoning impossible to change

☐ Costs more than budget

Other: __________________

SEARCH CHANNELS:

How will you find land?

☐ Realtor (find regenerative-friendly agent)

☐ Land.com / online search

☐ Word of mouth / local network

☐ Approaching landowners directly

☐ Working with land broker

☐ Conservation land (lower cost)

☐ Other: __________________

TIMELINE:

When do we want land under control?

Target month: __________ (e.g., month 9-12 of Spiral 2)

#### 3.2 LAND SOURCING PROCESS

Worksheet 3.2.A: Land Identified & Evaluated

When you find potential land, research & evaluate:

PROPERTY #: _____

Address/Location: ________________

Contact: __________________

List Price: $_________

Acres: ______

BASIC DATA:

☐ Zoning verified: ______________

☐ Access road confirmed: ✓

☐ Property lines clear: ✓

☐ Title clean: ✓ (verified by lawyer)

☐ Water source identified: ✓

Type: _____ (spring/creek/well/municipal)

Quantity: _____ gallons/day (estimate)

Quality: _____ (needs testing: yes/no)

☐ Electricity available: ☐ Yes ☐ No ☐ Can get

☐ Internet available: ☐ Yes ☐ No ☐ Can get

ENVIRONMENTAL:

☐ Environmental survey done: ✓

Findings: ________________

☐ Soil testing done: ✓

Results: ________________

☐ Wetlands present: ☐ Yes ☐ No

☐ Endangered species: ☐ Yes ☐ No

☐ Previous land use: ___________

☐ Contamination concerns: __________

TOPOGRAPHY:

☐ Elevation: _____ ft

☐ Slope: _____ % (steeper = more challenges)

☐ Best building sites identified: ✓

(southern exposure for passive solar)

☐ Food production areas suitable: ✓

☐ Water management (drainage, swales): ✓

FINANCIAL:

List price: $_________

Negotiated price: $_________

Down payment: $_________ (what % of price?)

Terms: __________________

Contingencies: __________________

Closing timeline: __________________

REGULATORY:

Zoning: __________________

Current allowed uses: __________________

Needed variance: ☐ Yes ☐ No

Variance timeline: __________________

Cost: $_________

Likelihood of approval: __________

COMMUNITY FIT:

Does it match our vision? ☐ Yes ☐ No ☐ Mostly

Pros: __________________

Cons: __________________

Overall assessment: __________________

DECISION:

☐ PURSUE - move forward with offer

☐ KEEP LOOKING - good but not ideal

☐ REJECT - not right for us

Next step: __________________

Timeline: __________________

#### 3.3 DUE DILIGENCE ON SELECTED PROPERTY

Worksheet 3.3.A: Comprehensive Site Assessment

Once you have a strong candidate, do deeper analysis.

SELECTED PROPERTY:

Address: ________________

Acreage: ______

Price: $_________

Owner contact: __________________

ENVIRONMENTAL DUE DILIGENCE:

☐ Phase 1 Environmental Assessment (done by professional)

Findings: _________________

☐ Soil testing (NPK, pH, contaminants)

Results: _________________

☐ Water testing (if well or surface water)

Potable? ☐ Yes ☐ No

Treatment needed? ☐ Yes ☐ No ☐ Unknown

☐ Wetlands survey

Findings: _________________

☐ Endangered species survey

Findings: _________________

Implications: _________________

TOPOGRAPHIC SURVEY:

☐ Professional survey completed

Cost: $_________

Findings: _________________

HYDROLOGICAL ASSESSMENT:

☐ Water source capacity assessment

Flow rate: _____ gallons/day (sustainable)

Seasonal variation: ______________

Sufficient for community? ☐ Yes ☐ No ☐ Marginal

☐ Groundwater depth

Depth: _____ feet

☐ Drainage patterns

Flooding risk: ☐ None ☐ Low ☐ Moderate ☐ High

Swale placement options: __________________

SOLAR/CLIMATE ASSESSMENT:

☐ Solar potential (south-facing for passive solar)

Best building sites: __________________

Annual kWh/sq meter: _________ (for solar design)

☐ Wind assessment

Average wind speed: _____ mph

Wind resource: ☐ Poor ☐ Fair ☐ Good

☐ Microclimate

Frost patterns: _________________

Wind exposure: _________________

SOIL ASSESSMENT:

☐ Professional soil analysis

Type(s): __________________

pH: _______

Organic matter: ______%

Contaminants: ☐ None ☐ Acceptable ☐ Concerning

☐ Food production viability

Can support sustainable agriculture? ☐ Yes ☐ No ☐ Marginal

Amendments needed: __________________

Years to establish soil health: _______

LEGAL/REGULATORY DUE DILIGENCE:

☐ Title search completed

Status: ☐ Clear ☐ Liens/encumbrances

Issues: __________________

☐ Zoning verification

Current: __________________

Allows community? ☐ Yes ☐ No ☐ With variance

☐ Deed restrictions/covenants

Restrictions: __________________

Impact on our vision: __________________

☐ Utilities assessment

Public water available? ☐ Yes ☐ No

Public sewer available? ☐ Yes ☐ No

Septic possible? ☐ Yes ☐ No ☐ Unknown

Electric grid access? ☐ Yes ☐ No

Internet available? ☐ Yes ☐ No ☐ Can get with cost $______

☐ Road access

Public road? ☐ Yes ☐ No

Private road condition: __________________

Road maintenance responsibility: __________________

MARKET DUE DILIGENCE:

☐ Comparable sales analysis

Similar properties selling for: $_________

Our price: $_________ (discount/premium?)

☐ Appraisal (if financing)

Appraised value: $_________

Lending risk: __________________

☐ Local market trends

Appreciating or declining? __________________

FINAL ASSESSMENT:

Strengths: __________________

Weaknesses: __________________

Risks: __________________

Opportunities: __________________

FINANCIAL DECISION:

Asking price: $_________

Max we'll pay: $_________

Offer price: $_________

Terms proposed: __________________

TEAM DECISION:

☐ PROCEED - make offer

☐ NEGOTIATE - go back with lower offer

☐ WALK AWAY - not right for us

Decision date: __________

Final sign-off from founding team: [names]

#### 3.4 LAND ACQUISITION PROCESS

Worksheet 3.4.A: Purchase or Lease Agreement

Once property is selected:

ACQUISITION STRATEGY:

☐ Purchase (traditional mortgage)

☐ Purchase (owner financing)

☐ Lease with option to buy

☐ Lease only (long-term)

☐ Donation/gift (rare)

☐ Hybrid: _________________

STRUCTURE:

Acquisition Entity: __________________

(Legal structure: ☐ LLC ☐ Co-op ☐ Trust ☐ Non-profit)

Purchase Price (if buying): $_________

Down Payment: $_________ (%: _____)

Financing Source: __________________

Loan amount: $_________

Interest rate: __________%

Terms: _____ years

If Seller Financing:

Terms offered: __________________

Interest rate: __________%

If Lease:

Annual rent: $_________

Term length: _____ years

Option to purchase: ☐ Yes ☐ No

Purchase price if exercised: $_________

CONTINGENCIES IN AGREEMENT:

☐ Environmental assessment (satisfactory to buyer)

☐ Zoning verification

☐ Title insurance

☐ Financing approval (if applicable)

☐ Inspections (structural, well, etc.)

☐ Closing timeline: _____ days

☐ Other: __________________

CLOSING TIMELINE:

Offer date: __________

Inspection period: _____ days

Environmental review: _____ days

Financing period: _____ days (if applicable)

Target closing: __________

LEGAL SUPPORT:

Lawyer retained: ☐ Yes ☐ No

Lawyer name: __________________

Cost estimate: $_________

Title company: __________________

POST-CLOSING:

☐ Title transferred and recorded

☐ Deed recorded in your name/entity

☐ Title insurance issued

☐ First visit to land as owners: [DATE]

### SPIRAL 2: GATE 3 CHECKPOINT

## "Land + Team + Capital Convergence"

Decision Point: Are we actually ready to commit to land AND secured funding sources?

This is the point of no return. After this gate, you're making serious financial commitments.

Exit Criteria - ALL MUST BE TRUE:

☐ Land under control (purchased, optioned, or lease agreement signed) ☐ Full environmental and legal due diligence completed ☐ Team expanded to include essential specialist roles:

- Architect/designer

- Systems engineer (water/energy/food)

- Lawyer (real estate + entity structure)

- Financial advisor/CFO

- Operator/project manager ☐ Capital sources identified (not necessarily secured, but pathways clear) ☐ Rough master plan sketches show land is viable ☐ Team alignment remains strong ☐ Everyone understands what comes next (deep design work)

Gate 3 Go/No-Go Decision:

GATE 3 ASSESSMENT:

Date: __________

Facilitator: __________

Land secured: ☐ YES ☐ NO

Property: ________________

Closing date: __________

Due diligence complete: ☐ YES ☐ NO

Issues resolved: ☐ YES ☐ NO

Problems: _____________________________

Team ready: ☐ YES ☐ NO

Specialist roles filled: ☐ YES ☐ NO

Missing expertise: _____________________________

Capital pathway clear: ☐ YES ☐ NO

Funding sources identified: _____________________________

GATE 3 DECISION:

☐ PROCEED to Spiral 3 (Deep design + capital campaign)

☐ PAUSE - need more preparation (timeline: ____)

☐ STOP - land or financing situation changed

If PAUSE: What's needed? __________________

Timeline: ______________

## SPIRAL 2: CONDITION SET 4

### Capital Pathway Clarity

Timeline: Months 6-12 (parallel with land search, but intensive after land secured)

#### 4.1 COMPREHENSIVE FINANCIAL MODEL

Worksheet 4.1.A: Detailed Capital Needs Assessment

This is much more detailed than Spiral 1's rough sketch.

DEVELOPMENT CAPITAL NEEDS:

LAND:

Purchase price: $_________

Due diligence/legal: $_________

Closing costs (title, etc.): $_________

TOTAL LAND: $_________

INFRASTRUCTURE (fixed - spreads across all residents):

Water systems:

Rainwater collection: $_________

Filtration/treatment: $_________

Storage: $_________

Distribution pipes: $_________

Subtotal: $_________

Energy systems:

Solar PV (kW): $_________ @ $____/W

Wind turbine (if applicable): $_________

Battery storage: $_________

Wiring/electrical: $_________

Subtotal: $_________

Food systems:

Land prep/clearing: $_________

Soil amendment: $_________

Perennials/trees: $_________

Irrigation: $_________

Infrastructure (compost, storage): $_________

Subtotal: $_________

Waste systems:

Septic/biodigestor: $_________

Treatment wetlands: $_________

Composting: $_________

Subtotal: $_________

Transportation:

Road/path construction: $_________

Parking/vehicle areas: $_________

Subtotal: $_________

TOTAL INFRASTRUCTURE: $_________

Per resident (÷ # residents): $_________

HOUSING:

Number of units: ____

Average cost per unit: $_________

Land prep per unit: $_________

Foundation/structure: $_________

Interior finishing: $_________

Utilities connection: $_________

Total housing: $_________

COMMON SPACES:

Community center: $_________

Kitchen/dining: $_________

Meeting rooms: $_________

Workshops/studios: $_________

Guest accommodations: $_________

Office/admin space: $_________

TOTAL COMMON: $_________

PROFESSIONAL SERVICES:

Architecture/design: $_________

Engineering: $_________

Legal (entity, permits, land): $_________

Project management: $_________

Construction oversight: $_________

TOTAL PROFESSIONAL: $_________

PERMITS & APPROVALS:

Zoning variance (if needed): $_________

Environmental permits: $_________

Building permits: $_________

Well/septic permits: $_________

TOTAL PERMITS: $_________

CONTINGENCY:

(usually 10-15% of hard costs)

Hard costs subtotal: $_________

Contingency @ 15%: $_________

TOTAL DEVELOPMENT CAPITAL: $_________

OPERATING CAPITAL (first 2 years):

Staff for early phase: $_________

Insurance: $_________

Utilities (while under construction): $_________

Administration: $_________

Maintenance: $_________

Marketing/outreach: $_________

Unexpected costs: $_________

TOTAL OPERATING CAPITAL: $_________

GRAND TOTAL CAPITAL NEEDED: $_________

#### 4.2 PHASED DEVELOPMENT STRATEGY

Worksheet 4.2.A: Phasing Capital Requirements

You don't need all capital upfront. Break it into phases.

PHASE 1: MINIMUM VIABLE (Year 1-2)

What gets built:

- Infrastructure for: _____ people

- Water for: _____ people

- Energy for: _____ people

- Housing for: _____ people

- Food production: _____ acres

- Common spaces: _________________

- Utilities/roads: _________________

Capital required Phase 1: $_________

How much is this of total? _____%

PHASE 2: EXPANSION (Year 2-3)

What gets added:

- Additional housing for: _____ people

- Additional food production: _____ acres

- Additional common spaces: _________________

- System upgrades: _________________

Capital required Phase 2: $_________

PHASE 3+: FULL VISION (Year 3+)

Completing to full design

Capital required Phase 3+: $_________

PHASING LOGIC:

Why this sequence? (infrastructure first, then housing, then amenities)

_____________________________

Dependencies between phases:

_____________________________

Trigger for moving to next phase:

- Phase 1→2: _________________

- Phase 2→3: _________________

#### 4.3 REVENUE MODEL & FINANCIAL SUSTAINABILITY

Worksheet 4.3.A: Operating Economics

ANNUAL OPERATING EXPENSES:

Salaries (management, maintenance, administration):

Manager: $_________

Maintenance person: $_________

Operations coordinator: $_________

(Total: $_________%)

Utilities (water, electricity): $_________

Insurance (property, liability): $_________

Permits & licenses: $_________

Professional services (legal, accounting): $_________

Maintenance & repairs: $_________

Food/supplies for common spaces: $_________

Marketing & outreach: $_________

Contingency (10-15%): $_________

TOTAL ANNUAL EXPENSES: $_________

REVENUE SOURCES:

From residents/members:

Monthly member dues/fees:

# of residents: ____

Monthly per person: $_________

Annual: $_________

Initial member investment/down payment:

(one-time, per person): $_________

From community businesses:

Farm products: $_________/year

Retreat center rental: $_________/year

Workshops/seminars: $_________/year

Coworking space rental: $_________/year

Product sales: $_________/year

Short-term rentals: $_________/year

Other business: $_________/year

Total business revenue: $_________

From external grants/funding:

Conservation grants: $_________

Community development grants: $_________

Other: $_________

Total external: $_________

TOTAL ANNUAL REVENUE: $_________

FINANCIAL VIABILITY:

Annual revenue - Annual expenses = $_________ (surplus/deficit)

☐ Surplus (sustainable!)

☐ Deficit (needs other funding sources)

If deficit, how to bridge?

- Reduce expenses? What areas? _________________

- Increase revenue? Which revenue streams? _________________

- Additional resident investment? $_________/person

#### 4.4 FUNDING SOURCES & STRATEGY

Worksheet 4.4.A: Capital Sourcing Strategy

TOTAL CAPITAL NEEDED: $_________ (from 4.1)

FUNDING SOURCE OPTIONS:

From Residents/Members:

- Investment per person: $_________

- # of people investing: _____

- Total from residents: $_________

Questions: How much can members afford?

Will they get equity/ROI?

If not sustainable, need external funding

From Founders/Early Team:

- Founder investment: $_________

- Sweat equity/unpaid labor value: $_________

- Connections/resources: $_________

- Total from founders: $_________

From Investors:

- Type: ☐ Friends & Family ☐ Angel ☐ Impact Investors ☐ VC

- Amount sought: $_________

- Terms offered:

- Equity stake: _____%

- Return timeline: _____ years

- Exit strategy: _________________

- Repayment if not in equity: _________

From Banks/Lenders:

- Loan amount: $_________

- Interest rate: __________%

- Term: _____ years

- Monthly payment: $_________

- Collateral offered: _________________

From Grants:

- Conservation grants: $_________

- Community development: $_________

- Government programs: $_________

- Foundation funding: $_________

- Search tools: GrantStation, Foundation Center, USASpending

From Crowdfunding:

- Platform (Kickstarter, Indiegogo, etc.): _________________

- Amount target: $_________

- Offer: _________________

(equity, product, naming rights, etc.)

From Pre-sales:

- Selling lots/plots in advance: $_________

- Selling memberships: $_________

- Selling retreat packages: $_________

From Hybrid Structures:

- Community shares: $_________

- Debt + equity mix: _________________

- Phased fundraising: _________________

FUNDING MIX DECISION:

Total needed: $_________

Funding source breakdown:

- From residents: $_________ (____%)

- From founders: $_________ (____%)

- From investors: $_________ (____%)

- From banks: $_________ (____%)

- From grants: $_________ (____%)

- From crowdfunding: $_________ (____%)

- From other: $_________ (____%)

Total: $_________ (should = needed amount)

Does it add up? ☐ Yes ☐ No

If not, what's the gap? $_________

How will you bridge it?

_____________________________

#### 4.5 INVESTOR PITCH & PROSPECTUS

Worksheet 4.5.A: Investment Offering Document (Summary)

PROJECT:

Name: _______________________

Location: __________________

When will it be ready: __________

THE OPPORTUNITY:

(Why would someone invest in this?)

_____________________________

THE TEAM:

(Who's running this? Why should we trust them?)

- Founder 1: _____________ (experience: _________)

- Founder 2: _____________ (experience: _________)

- Key specialist: _____________ (expertise: _________)

THE MARKET:

(Who wants to live here?)

- Target market: _____________

- # of interested people: _____

- Market demand: _____________

THE BUSINESS MODEL:

(How will it make money?)

- Primary revenue: _____________

- Secondary revenue: _____________

- Annual revenue potential: $_________

THE INVESTMENT:

(What are we offering investors?)

- Amount needed: $_________

- What we're offering: (equity/debt/hybrid) _____________

- Terms: _________________

- Return timeline: _____________

- Use of funds:

- Land: $_________

- Infrastructure: $_________

- Working capital: $_________

THE RETURNS:

(How do investors make money?)

Scenario 1 (conservative):

Timeline: _____ years

Projected return: ____% or $__________

Scenario 2 (expected):

Timeline: _____ years

Projected return: ____% or $__________

Scenario 3 (optimistic):

Timeline: _____ years

Projected return: ____% or $__________

EXIT STRATEGY:

(How can investors get their money back?)

- Buyback from community

- Secondary sale of equity

- Dividend/revenue share

- Real estate appreciation

- Other: _________________

THE IMPACT:

(What good does this do?)

- Environmental impact: _________________

- Social impact: _________________

- Economic impact: _________________

RISK DISCLOSURE:

(Be honest about risks)

- Market risks: _________________

- Construction risks: _________________

- Team/leadership risks: _________________

- Regulatory risks: _________________

- Financial risks: _________________

- Mitigation strategies: _________________

NEXT STEPS FOR INVESTORS:

- Due diligence documents available

- Reference communities available

- Founder meetings: when/where

- Legal review: by investor's attorney

- Decision timeline: _________________

CONTACT:

Primary contact: __________________

Email: __________________

Phone: __________________

### SPIRAL 2: SUMMARY & DELIVERABLES

Timeline: 3-12 months (typical 6-9 months; land search often longest piece)

Major Deliverables Produced:

- ✓ Land Assessment Reports (environmental, soil, water, regulatory)

- ✓ Land Secured (purchased, optioned, or lease agreement signed)

- ✓ Detailed Financial Model (capital needed, phasing, operating budget)

- ✓ Revenue Model (how project becomes self-sustaining)

- ✓ Funding Strategy (specific sources, amounts, terms)

- ✓ Investment Prospectus (pitch document for capital)

- ✓ Preliminary Master Plan (showing site viability)

- ✓ Team Expansion (specialists now on board)

Team Composition After Spiral 2:

- Core 5-7 founders plus:

- Architect/designer

- Systems engineer

- Lawyer

- Financial advisor

- Possibly project manager

- Plus 25-50 interested community members

Budget Spent: $50,000-$200,000 (land assessments, legal, professional services, travel)

Ready for Spiral 3? YES → Proceed to Deep Design & Capital Campaign

# SPIRAL 3: CAPITAL OPTIMIZATION

## Months 9-15 | Goal: Capital Secured + Operations Ready

Objective: Raise capital, finalize operational design, activate early community

Success Looks Like: Funding closed, team trained, early events happening, ready to break ground

## SPIRAL 3: CONDITION SET 5 & 6 & 7

### Team Expansion, System Integration, Operational Readiness

Timeline: Months 9-15 (parallel with capital campaign)

#### 5.1 SPECIALIST TEAM RECRUITMENT

Worksheet 5.1.A: Team Roles & Responsibility Matrix

By now you need a larger team. Define roles:

FOUNDING TEAM (core 5-7):

[Names from previous spirals]

SPECIALIST ROLES TO FILL:

Architect/Master Planner:

☐ Hired / ☐ Identified / ☐ Searching

Name: __________________

Expertise: __________________

Compensation: $_________ (project-based) or ___% equity

Start date: __________

Responsibilities:

- Master plan design

- Building layouts

- Integration of all systems

Systems Engineer (Water/Energy/Food):

☐ Hired / ☐ Identified / ☐ Searching

Name: __________________

Expertise: __________________

Compensation: $_________

Start date: __________

Responsibilities:

- Detailed system design

- Material/equipment specs

- Cost/performance analysis

Real Estate Lawyer:

☐ Hired / ☐ Identified / ☐ Searching

Name: __________________

Expertise: __________________

Compensation: $_________

Start date: __________

Responsibilities:

- Legal entity formation

- Land agreements

- Zoning/permits

- Community agreements/bylaws

Financial Advisor / CFO:

☐ Hired / ☐ Identified / ☐ Searching

Name: __________________

Expertise: __________________

Compensation: $_________

Start date: __________

Responsibilities:

- Financial modeling

- Investor relations

- Accounting systems

- Budget management

Project Manager / Operations:

☐ Hired / ☐ Identified / ☐ Searching

Name: __________________

Expertise: __________________

Compensation: $_________

Start date: __________

Responsibilities:

- Construction management

- Schedule coordination

- Vendor/contractor relations

- Day-to-day operations

Governance Facilitator / Mediator:

☐ Hired / ☐ Identified / ☐ Searching

Name: __________________

Expertise: __________________

Compensation: $_________

Start date: __________

Responsibilities:

- Governance design

- Conflict resolution

- Team training

- Culture facilitation

DECISION-MAKING AUTHORITY MATRIX:

(Who decides what? Fill in names)

Land decisions: __________

Design decisions: __________

Budget decisions: __________

Hiring decisions: __________

Conflict resolution: __________

Culture/community: __________

Governance structure: __________

Strategic pivots: __________

Timeline: __________

#### 5.2 TEAM GOVERNANCE TRAINING

Worksheet 5.2.A: Governance Workshop Agenda

Task: Before capital campaign, team needs to practice making decisions.

GOVERNANCE TRAINING SESSION:

Date/time: __________________

Facilitator: __________________

Duration: 2-3 days

AGENDA:

Day 1: Decision-Making Models

- Consensus vs. consent vs. voting

- Your chosen model (refresh)

- Practicing decisions together

- Common mistakes

Exercise 1: Practice Decision

Decision to make: [pick something real]

Timeline: 1 hour

Model: [your chosen approach]

Debrief: What worked? What was hard?

Day 2: Conflict Resolution

- Types of conflict (task, interpersonal, procedural)

- Non-violent communication basics

- 5-step conflict resolution process

- Mediator role

Exercise 2: Practice Conflict

Scenario: [real tension from team]

Process: [your conflict resolution method]

Debrief: Could you resolve it? What helped?

Day 3: Ongoing Operations

- Decision documentation

- Meeting cadence & format

- Communication channels

- Feedback & adaptation

- Governance evolution

OUTCOME:

☐ All team members understand model

☐ Team has practiced making decisions

☐ Conflict resolution process tested

☐ Everyone confident in governance

#### 5.3 COMMUNITY PRE-LAUNCH & CULTURE SEEDING

Worksheet 5.3.A: Early Community Activation Plan

Idea: Don't wait until occupancy to build culture. Start now.

EARLY COMMUNITY EVENTS:

Vision Event #1 (Month 10):

- Type: ☐ Gathering ☐ Workshop ☐ Work party ☐ Celebration

- Who: Founders + interested community members

- Where: [land/meeting space]

- When: ___________________

- What: _____________________

(Share vision, walk land, build excitement)

- Attendance target: _____ people

- Outcome: _____________________

Vision Event #2 (Month 12):

- Type: ☐ Gathering ☐ Workshop ☐ Work party ☐ Celebration

- What: _____________________

(Progress update, deeper exploration, community building)

Vision Event #3 (Month 14):

- Type: ☐ Gathering ☐ Workshop ☐ Work party ☐ Celebration

- What: _____________________

(Celebrate capital raised, build momentum)

CULTURE FOUNDATION:

Community values being lived now:

- How do we show our values in these early events?

Example: If sustainability is a value, serve local vegan food

Your culture foundation: _____________________

Communication norms being established:

- How do we communicate (channels, frequency, style)?

_____________________

Decision-making being practiced:

- What small decisions does the wider community help make?

(garden design, event planning, etc.)

_____________________

Community culture canvas review:

☐ Revisited from Spiral 1

☐ Still accurate? ☐ Yes ☐ No

☐ Changes needed: _____________________

Early community coordinator:

- Person responsible for seeding culture: __________

- Title: Community Builder / Host

- Time: ____ hours/week

- Focus: Building relationships, sense of belonging

#### 5.4 OPERATIONAL SYSTEMS DESIGN

Worksheet 5.4.A: Operations Manual (Outline)

Design how the community will actually run (before you're running it).

OPERATIONS MANUAL OUTLINE:

Chapter 1: GOVERNANCE

- Decision-making process (flow chart)

- Voting/consensus method (detailed)

- Committee structure

- Dispute resolution process

- Member rights/responsibilities

Chapter 2: MEETINGS

- Weekly meeting agenda & format

- Monthly all-hands agenda

- Work group/committee meetings

- Decision documentation

- Archive system

Chapter 3: MEMBERSHIP

- Member types (resident, associate, investor, etc.)

- Onboarding process (step-by-step)

- Orientation checklist

- Ongoing member expectations

- Offboarding process

Chapter 4: FINANCES

- Budget process

- Expense approval (who signs what amount)

- Income sharing (if applicable)

- Accounting system & software

- Financial reporting (how often, to whom)

- Audit process

Chapter 5: FACILITIES & MAINTENANCE

- Maintenance responsibilities (who does what)

- Maintenance schedule (daily, weekly, monthly, seasonal)

- Work party system (if applicable)

- Maintenance request process

- Emergency procedures

Chapter 6: COMMUNICATION

- Communication channels (Slack, email, etc.)

- Communication norms (response time, respectful dialogue)

- Board/announcements

- Newsletter/updates (frequency, format)

- Internal directory

Chapter 7: COMMUNITY CULTURE

- Values & agreements

- Rituals & celebrations

- Conflict resolution (detailed)

- Accountability process

- Cultural evolution

Chapter 8: EMERGENCY PROCEDURES

- Fire/safety

- Medical

- Weather/natural disaster

- Community crisis/conflict

Chapter 9: POLICIES

- Pets

- Visitors/guests

- Noise/nuisance

- Parking (if applicable)

- Use of common spaces

- Smoking/substances (if applicable)

Chapter 10: SUSTAINABILITY

- Water usage & conservation

- Energy usage & conservation

- Waste/recycling

- Food systems

- Environmental practices

STATUS:

☐ Draft outline created

☐ Assigned writers to each chapter

☐ Timeline for completion: __________

☐ Review/finalization: __________

#### 6.1 SYSTEM INTEGRATION: THE MASTER PLAN

Worksheet 6.1.A: Master Plan Elements Checklist

This is the deepest design work. All systems must integrate.

MASTER PLAN COMPONENTS:

ECOLOGY LAYER:

☐ Ecological baseline assessment

- Current vegetation/habitat

- Wildlife patterns

- Water cycle mapping

- Soil analysis

☐ Restoration plan

- What will we restore?

- Success metrics

- Timeline

☐ Regenerative targets

- Biodiversity goals

- Soil carbon sequestration targets

- Water cycle closure goals

- Carbon footprint reduction

WATER SYSTEM INTEGRATION:

☐ Rainfall data & seasonal patterns

☐ Collection points & capacity

- Rooftop area: _____ sq ft

- Ground catchment: _____ sq ft

- Annual collection potential: _____ gallons

☐ Storage (tank size): _____ gallons

- Seasonal variation accommodation

- Redundancy/backup

☐ Treatment pathway

- Potable water: _____ gallons/day

- Greywater: _____ gallons/day

- Blackwater: _____ gallons/day

☐ Recycling cascade

- Potable → Greywater → Irrigation → Wetland → Infiltration

ENERGY SYSTEM INTEGRATION:

☐ Energy consumption estimate

- Homes: _____ kWh/day

- Common spaces: _____ kWh/day

- Total: _____ kWh/day

- Annual: _____ kWh/year

☐ Solar resource

- Best south-facing areas identified

- Rooftop capacity: _____ kW

- Ground mount capacity: _____ kW

- Total design: _____ kW

- Annual generation: _____ kWh

☐ Battery storage

- Capacity: _____ kWh

- Days of autonomy: _____

☐ Grid connection

- Grid tie with backup ☐ or Off-grid ☐

- Net metering possible? ☐ Yes ☐ No

☐ Load reduction strategies

- Passive solar design

- Efficient appliances

- Occupant behavior

FOOD SYSTEM INTEGRATION:

☐ Population to feed: _____ people

☐ Caloric needs: _____ calories/person/day = _____ total/day

☐ Land available: _____ acres

☐ Proposed breakdown:

- Annual vegetables: _____ acres

- Perennial food (forest/agroforestry): _____ acres

- Livestock (if any): _____ acres

☐ Seasonal production plan

- Spring crops: _____

- Summer crops: _____

- Fall crops: _____

- Winter crops/storage: _____

☐ Integration with water system

- Irrigation water source: graywater ☐ rainwater ☐ both

- Composting from waste → soil building

☐ Integration with energy system

- Food processing (electricity needed): _____

- Cold storage/preservation: _____

- Irrigation pumping: _____

☐ Self-sufficiency targets

- % of food produced on-site: ____% (year 1) → ____% (year 3)

- Key crops for nutrition:

- Protein: _____

- Carbs: _____

- Fats: _____

- Micro-nutrients: _____

WASTE SYSTEM INTEGRATION:

☐ Organic waste streams

- Food scraps: _____ lbs/day

- Garden waste: _____ lbs/day

- Human waste: _____ people

☐ Processing pathway

- Composting facility size: _____

- Biodigester (if blackwater): _____

- Treatment wetlands: _____ sq ft

☐ Outputs

- Compost for gardens: _____ cubic yards/year

- Nutrient water for irrigation: _____ gallons/year

☐ Inorganic waste

- Recycling infrastructure

- Zero-waste targets: ____% diversion

HOUSING & BUILT ENVIRONMENT:

☐ Building count: _____ structures

☐ Unit breakdown:

- Single-family homes: _____

- Duplexes: _____

- Apartments: _____

- Guest/visitor housing: _____

- Common spaces: _____

☐ Spatial organization

- Pedestrian zones (car-free): _____ sq ft

- Vehicle zones (limited): _____ sq ft

- Private space (yards): _____ sq ft

- Common gathering space: _____ sq ft

☐ Building design principles

- Passive solar orientation

- Natural ventilation strategy

- Thermal mass for climate

- Daylighting

- Local/natural materials

- Adaptability/flexibility for future changes

☐ View/aesthetics

- Sight lines to landscape

- Building materials cohesion

- Public art/design features

TRANSPORTATION & CIRCULATION:

☐ Road/path network

- Main road: width _____, surface _____

- Secondary paths: width _____, surface _____

- Pedestrian paths: width _____, surface _____

☐ Parking

- # of spaces: _____ (1 per ____ residents)

- Location: (centralized or distributed?)

- Design: (visible or hidden?)

☐ EV charging (if applicable)

- # of charging stations: _____

- Location: _____

GOVERNANCE INTEGRATION INTO SPACE:

☐ Spaces for key governance functions

- Council room (capacity): _____

- Conflict resolution space: _____

- Decision-making documentation system

☐ Communication infrastructure

- Bulletin boards/signage locations

- Digital infrastructure (WiFi, servers)

- Community broadcast space (all-hands meetings)

CULTURE INTEGRATION:

☐ Spaces that support community values

- If value is "local food": kitchen is central, not hidden

- If value is "transparency": decision-making spaces visible

- If value is "celebration": gathering spaces plenty

☐ Ritual/ceremony spaces

- Gathering fire/circle space

- Seasonal celebration area

☐ Arts/creativity spaces

- Studio spaces (music, art, craft)

- Performance space

☐ Learning spaces

- Workshop areas

- Library/knowledge commons

ECONOMIC INTEGRATION:

☐ Revenue-generating businesses built into site

- Farm stand location (visibility, accessibility)

- Retreat center location (separate from residential, serene)

- Workshops/classes space

- Visitor accommodation location

☐ Job creation within community

- # of jobs created: _____

- Types: _____

- Hours: _____ (full-time/part-time/both)

PHASING SEQUENCE ON SITE:

Phase 1 (Year 1-2):

- Infrastructure: ___________

- Housing for ____ people

- Common spaces: __________

Phase 2 (Year 2-3):

- Additional housing for ____ people

- Additional: __________

Phase 3 (Year 3+):

- Completion to full vision

Why this sequence?

_____________________________

DESIGN QUALITY CHECK:

☐ All systems feed each other (no silos)

☐ Water system informs habitat informs food informs energy

☐ Governance enables ecological goals

☐ Economy rewards regeneration

☐ Technology supports (doesn't control)

☐ Humans relate well to each other and land

☐ Resilience built in (can handle disruptions)

IMPACT TARGETS (at build-out):

Ecological:

- Carbon neutral: ☐ Year ____ or ☐ Already

- Water cycle closure: ____ %

- Biodiversity improvement: ____% more species

- Soil regeneration: ____  tons C/acre/year

Community:

- Member satisfaction: ____% happy/thriving

- Retention rate: ____% stay 3+ years

- Belonging/connection: ____% feel strong community

Economic:

- Self-sufficiency: ____% of income from on-site

- Job creation: _____ jobs

- Revenue from businesses: $_________/year

Social/Cultural:

- Diversity: representation of ____

- Leadership development: _____ people trained

- Knowledge sharing: _____ workshops/year

#### 7.1 LEGAL & ENTITY STRUCTURE

Worksheet 7.1.A: Organizational Structure Decision

LEGAL ENTITY FORMATION:

Land Holding Structure:

☐ Community Land Trust

- Tax advantages: non-profit 501(c)(3)

- Control: Residents own buildings, trust owns land

- Affordability: Built-in via CLT model

- Land use restrictions: Permanent

☐ Cooperative

- Tax advantages: pass-through entity

- Control: One member, one vote

- Affordability: Member equity cooperative

- Land use: Democratic control

☐ LLC

- Tax advantages: pass-through entity

- Control: Members by agreement

- Affordability: Set by business model

- Land use: Flexible

☐ Non-Profit Organization (501(c)(3))

- Tax advantages: Full non-profit status

- Control: Board governance

- Affordability: Can require low-income percentage

- Land use: Mission-driven restrictions

☐ Hybrid Model: ________________

Example: Non-profit land trust + resident co-op for buildings

SELECTED STRUCTURE: __________________

Why this model? _____________________

Operations/Member Entity:

(Separate from land-holding entity)

☐ Homeowners Association

☐ Cooperative

☐ Non-profit

☐ Informal consensus group

☐ Other: __________________

GOVERNANCE DOCUMENT:

Type: ☐ Bylaws ☐ Operating Agreement ☐ Covenants ☐ Constitution

Key inclusions:

☐ Purpose/mission statement

☐ Member rights & responsibilities

☐ Decision-making process

☐ Dispute resolution

☐ Amendment process

☐ Dissolution/succession

☐ Sustainability covenants (ecological commitments)

☐ Affordability provisions

☐ Community agreements

☐ Financial policies

LEGAL FORMATION CHECKLIST:

☐ Entity incorporated with state

☐ EIN (Employer ID Number) obtained

☐ Bylaws/operating agreement drafted & signed

☐ 501(c)(3) status applied for (if applicable)

☐ Bank account opened

☐ Insurance obtained

☐ Community agreements drafted

☐ Land transfer completed to entity

LAWYER:

Name: __________________

Specialty: Real estate / Cooperative law

Engagement: Started ☐ Completed ☐

Cost: $_________

### SPIRAL 3: GATE 5 CHECKPOINT

## "Capital Assembled + Leadership Ready"

Decision Point: Are we funded and ready to build?

Exit Criteria - ALL MUST BE TRUE:

☐ 70%+ of development capital secured (not 100% - phased approach works) ☐ Core team trained in governance and decision-making ☐ Specialist roles filled (architect, engineer, lawyer, CFO, operator) ☐ Operational manuals drafted ☐ Master plan complete and detailed ☐ Legal entities established ☐ Insurance obtained ☐ Regulatory approvals in process (building permits, zoning, etc.) ☐ Early community events happening ☐ Community momentum building (member list growing)

Gate 5 Go/No-Go Decision:

GATE 5 ASSESSMENT:

Date: __________

Facilitator: __________

Capital status:

- Total needed: $_________

- Capital secured: $_________

- % secured: ____% (need 70%+)

Decision: ☐ YES ☐ NO

Team readiness:

- Governance training: ☐ Completed

- Specialist roles: ☐ All filled

- Team alignment: ☐ Strong

Decision: ☐ YES ☐ NO

Design completion:

- Master plan: ☐ Complete & detailed

- Systems integrated: ☐ Yes

- Operations manuals: ☐ Drafted

Decision: ☐ YES ☐ NO

Regulatory status:

- Zoning variance (if needed): ☐ Approved

- Building permits (ready to apply): ☐ Yes

- Other approvals: ☐ In process

Decision: ☐ YES ☐ NO

Community momentum:

- Early events: ☐ Happening

- Member interest: ☐ Growing

- Cultural foundation: ☐ Seeded

Decision: ☐ YES ☐ NO

GATE 5 DECISION:

☐ PROCEED to Spiral 4 (Construction)

☐ PAUSE - need more funding time (timeline: ____)

☐ STOP - major obstacle discovered

Next phase start date: __________

## SPIRAL 3: SUMMARY & DELIVERABLES

Timeline: 9-15 months

Major Deliverables:

- ✓ Capital Secured (70%+)

- ✓ Detailed Master Plan

- ✓ Operations Manual (drafted)

- ✓ Legal Entities Established

- ✓ Team Trained in Governance

- ✓ Specialist Roles Filled

- ✓ Regulatory Approvals In Process

- ✓ Early Community Activated

Budget Spent: $100,000-$500,000 (professional fees, permits, early events, advance payments on contracts)

Ready for Spiral 4? YES → Proceed to Construction

# SPIRAL 4: CONSTRUCTION & OPERATION

## Months 12-36 | Goal: Build & Occupy Community

Objective: Execute construction in phases, activate culture while building, learn and adapt

Success Looks Like: Phase 1 residents moved in, systems operational, culture alive

## SPIRAL 4: CONDITION SET 8

### Physical Systems Operational

This is not detailed here (too much variation by project), but the framework:

PHASE 1 CONSTRUCTION:

Timeline: Months 12-24

What gets built:

- Infrastructure for ____ people

- Housing for ____ people

- Common spaces for: _______

Gates during construction:

- Permit approval: [date]

- Ground breaking: [date]

- Infrastructure milestone 1: [date]

- First occupancy: [date]

- Full Phase 1 occupancy: [date]

Learning cycles during construction:

- Monthly community update meetings

- After each major milestone, pause and reflect

- "What did we learn?" incorporated into next phase

# SPIRAL 5: CONTINUOUS REGENERATION

## Year 2+ | Goal: Measure Impact & Continuously Improve

Objective: Validate regenerative impact, document learnings, share with broader movement

## SPIRAL 5: CONDITION SET 9

### Regenerative Performance

Worksheet 9.1.A: Impact Measurement Dashboard

ECOLOGICAL METRICS:

Soil Carbon Sequestration:

- Baseline (Year 0): _____ tons C/acre

- Year 1 target: _____ tons C/acre

- Year 2 actual: _____ tons C/acre

- Year 3 actual: _____ tons C/acre

- Status: ☐ On track ☐ Ahead ☐ Behind

Water Cycle Closure:

- Baseline rainfall: _____ in/year

- Baseline infiltration: ____% of rainfall

- Year 1 target: ____% infiltration

- Actual achieved: ____% infiltration

- Status: ☐ On track ☐ Ahead ☐ Behind

Biodiversity:

- Baseline species count: _____

- Target increase: ____%

- Actual increase: ____%

- Status: ☐ On track ☐ Ahead ☐ Behind

COMMUNITY METRICS:

Member Satisfaction:

- Baseline survey (Year 1): _____ % satisfied

- Year 2 survey: _____ % satisfied

- Target: 80%+ satisfied

- Status: ☐ On track ☐ Ahead ☐ Behind

Belonging/Connection:

- "I feel strong sense of belonging": _____ % agree

- Target: 70%+ agree

- Status: ☐ On track ☐ Ahead ☐ Behind

Retention Rate:

- Members staying 2+ years: _____ %

- Target: 70%+

- Status: ☐ On track ☐ Ahead ☐ Behind

ECONOMIC METRICS:

Financial Sustainability:

- Annual revenue: $_________

- Annual expenses: $_________

- Surplus/deficit: $_________

- Self-sustaining yet? ☐ Yes ☐ No ☐ Close

Jobs Created:

- Jobs offered: _____

- Jobs filled: _____

- Average wage: $_________

- Career development happening: ☐ Yes ☐ No

SOCIAL/CULTURAL METRICS:

Diversity & Inclusion:

- Racial diversity: ____%

- Income diversity: ____%

- Age diversity: ____%

- Target: Reflect broader community

- Status: ☐ On track ☐ Need improvement

Leadership Development:

- New leaders developed: _____

- Leadership training: ____ events/year

- Rotating roles happening: ☐ Yes ☐ No

Knowledge Sharing:

- Workshops/events hosted: ____ /year

- Visitors/tours: ____ /year

- Publications/case studies: _____

- Contributing to broader movement: ☐ Yes ☐ No

LEARNING & ADAPTATION:

What's worked better than expected:

_____________________________

What's been harder than expected:

_____________________________

What we're changing for year 2:

_____________________________

How we're sharing learnings:

☐ Case study documentation

☐ Website/blog updates

☐ Speaking at conferences

☐ Academic research

☐ Framework contribution

# APPENDIX: QUICK REFERENCE TEMPLATES

## Master Checklist: All Spirals

### SPIRAL 1: PROOF-OF-CONCEPT (Months 0-6)

Condition Set 1: Core Team Coherence ☐ 5-7 founders assembled ☐ Individual vision interviews done ☐ Shared values statement drafted & signed ☐ Decision-making approach documented ☐ Communication systems established Gate 1 Decision: Proceed / Pause / Stop

Condition Set 2: Market & Feasibility Exploration ☐ Target community profile defined ☐ 20-30 market validation interviews done ☐ 3-5 bioregions researched ☐ Climate & water viability assessed ☐ Regulatory landscape mapped ☐ Rough financial model sketched ☐ Proof-of-concept design drawn Gate 2 Decision: Proceed / Pivot / Stop

### SPIRAL 2: FEASIBILITY VALIDATION (Months 3-12)

Condition Set 3: Land Identification & Assessment ☐ Land search strategy documented ☐ Multiple properties evaluated ☐ Selected property: full due diligence completed ☐ Environmental assessment ☐ Soil testing ☐ Water assessment ☐ Title/legal clear ☐ Zoning verified ☐ Land under control (purchased/optioned/leased)

Condition Set 4: Capital Pathway Clarity ☐ Detailed capital needs calculated ($________) ☐ Phased development strategy planned ☐ Operating budget estimated ☐ Revenue model designed ☐ Funding sources identified ☐ Investment prospectus drafted Gate 3 Decision: Proceed / Pause / Stop

### SPIRAL 3: CAPITAL OPTIMIZATION (Months 9-15)

Condition Set 5: Team Expansion & Readiness ☐ Architect hired ☐ Systems engineer hired ☐ Lawyer hired ☐ CFO/financial advisor hired ☐ Project manager hired ☐ Governance facilitator identified ☐ Governance training completed ☐ Team alignment strong

Condition Set 6: System Integration ☐ Master plan complete & detailed ☐ Water system integrated ☐ Energy system integrated ☐ Food system integrated ☐ Waste system integrated ☐ Housing/layout integrated ☐ Transportation integrated ☐ Governance space integrated ☐ Culture space integrated ☐ Economic integration checked

Condition Set 7: Operational Readiness ☐ Legal entities established ☐ Insurance obtained ☐ Governance documents finalized ☐ Operations manuals drafted ☐ Early community events happening ☐ Member pre-registration beginning ☐ Regulatory approvals in process ☐ Capital raised (70%+) Gate 5 Decision: Proceed / Pause / Stop

### SPIRAL 4: CONSTRUCTION & OPERATION (Months 12-36+)

Condition Set 8: Physical Systems Operational ☐ Phase 1 construction complete ☐ Water system producing ☐ Energy system producing ☐ Housing habitable ☐ Common spaces functional ☐ First residents moved in ☐ Operations procedures being practiced ☐ Culture manifesting ☐ Governance decisions being made ☐ Baseline metrics established

### SPIRAL 5: CONTINUOUS REGENERATION (Year 2+)

Condition Set 9: Regenerative Performance ☐ Ecological metrics showing improvement ☐ Community metrics showing thriving ☐ Economic viability demonstrated ☐ Cultural life rich & evolving ☐ Learnings documented ☐ Contributing to broader movement ☐ Ready to replicate or expand

## Timeline at a Glance

MONTH 0    MONTH 6    MONTH 12   MONTH 18   MONTH 24   MONTH 36   YEAR 4

Spiral 1   Spiral 2   Spiral 3   Spiral 4   Spiral 4   Spiral 4   Spiral 5

■■■■■■■    ■■■■■■■■   ■■■■■■■    ■■■■■■■■■■■■■■■■■■■■■■■■■■■■

(Land)           (Construction)              (Operations)

Gate 1     Gate 2     Gate 3     Gate 5

↓          ↓          ↓          ↓

PROCEED    PROCEED    PROCEED    PROCEED

## Success Metrics by Spiral

| Spiral | Key Deliverable | Success Metric |
| --- | --- | --- |
| 1 | Shared vision | Team alignment score 8+/10 |
| 2 | Land secured | Land under control by month 12 |
| 3 | Capital raised | 70%+ of capital secured |
| 4 | Community occupied | First residents moved in by month 24-30 |
| 5 | Impact measured | Ecological metrics improving year-over-year |

## Budget Summary

| Spiral | Typical Investment | What It Buys |
| --- | --- | --- |
| 1 | $2,000-$10,000 | Professional consultations, travel, basic due diligence |
| 2 | $50,000-$200,000 | Environmental surveys, legal, specialized assessments |
| 3 | $100,000-$500,000 | Professional design, permits, early capital campaign |
| 4 | $500,000-$5,000,000+ | Land, construction, infrastructure, staffing |
| Total | $650K-$5.7M | Depends heavily on land price & scope |

## Key Success Factors Across All Spirals

- Experienced Facilitator - Someone who's built community or complex projects before

- Clear Decision-Making - Don't let meetings become endless debates

- Realistic Timelines - Don't try to rush (especially land search)

- Continuous Feedback - After each sprint, pause and learn

- Early Culture Seeding - Don't wait for perfect conditions

- Transparency - Share challenges openly, not just wins

- Adaptability - Be ready to modify plans based on learnings

- Celebration - Mark milestones and appreciate progress

## When to Pause or Stop

PAUSE (take more time) when:

- Team alignment is weak - worth investing time here

- Market validation unclear - don't guess

- Land not right - better to wait than be stuck with wrong land

- Capital strategy uncertain - don't start construction underfunded

- Governance not practiced - test it first

STOP when:

- Fundamental misalignment in team on core values

- Market shows no actual demand (interviews say no)

- Regulatory environment fundamentally blocks vision

- Capital cannot be raised

- Land is not available at any price

## Continuous Improvement Framework

After each gate:

GATE REVIEW MEETING:

1. ASSESS:

- Did we meet exit criteria? (yes/no/partial)

- What evidence supports this?

2. CELEBRATE:

- What did we accomplish?

- Who should be recognized?

3. LEARN:

- What surprised us?

- What was harder than expected?

- What was easier than expected?

- What should we do differently next time?

4. DECIDE:

- Do we proceed? (yes/conditional/no)

- If conditional, what conditions must be met?

- What's the new timeline?

5. COMMIT:

- Who's responsible for next steps?

- What's the next checkpoint?

- How do we stay accountable?

This completes the full hybrid sequencing model.

Ready to use. Adaptable to any context.

The framework is alive - iterate, learn, improve, and share back.